## Timesheet (hidden)
pin | Domain Name | 2025-03-11 |  | 2025-03-12 |  | 2025-03-13 |  | 2025-03-14 |  | 2025-03-15 |  | 2025-03-16 |  | 2025-03-17 |  | 2025-03-18 |  | 2025-03-19 |  | 2025-03-20 |  | 2025-03-21 |  | 2025-03-22 |  | 2025-03-23 |  | 2025-03-24 |  | 2025-03-25 |  | 2025-03-26 |  | 2025-03-27 |  | 2025-03-28
|  | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status
1 | Anagha.Shinde | NA |  | NA | on leave | NA | on leave | NA | PH | NA |  | NA |  | Refer the wireframes (low-fidelity)shared by product. | Completed | Ideate the color schemes / theme of the website using the key elements and inputs given, post discussion with product. | Completed | Mid fidelity wireframe implementation | Completed | Design iterations for Player cards | Completed | Design iteration for player cards and player details. Cross communication with frontend devs (Umkant, Shubham) | Completed | NA |  | NA |  | Design iteration for Admin side. 1. Add tournament 2. Add Player | Completed | Discussion of desgin implementation with devs (Umakant, Shubham, Jaypal) Work on feedback and suggestions from the devs. | completed | Design iteration for Admin side Discussion with devs | In progress | Design disscussions and ideation for credits page | In progress | Design iteration for login: 1.Login Page 2.Forgot Password page: Take email as input 3.Enter OTP page: 6 digit OTP Create new password page: Two 4.input fields: Enter Password and Confirm Password | In progress
2 | Anushree1.Shukla | NA | on leave | NA | on leave | NA | on leave | NA | on leave | NA | on leave | NA | on leave | NA | on leave | NA |  | NA |  | NA |  | 1. Had a discussion with Omakr and Sejal regarding my contribution in Bi-Weekly 2. came with ideas for the dashboard of chatbot analysis using MPC and Team Data | completed | no task implemented |  | no task implemented |  | 1. made sheets for prompts and generated around 100 prompts to run in chatbot in diffrent categories 2. succussfully made 100 prompts in different category for chatbot | Completed | 1. started working on the dashboard with Sanjeev 2. came up with ideas how data can be presented | completed | 1. Still worked on dashboard on power bi in morning 2. completed dashboard making by EOD | Completed | 1. Got dashboard reviewed by Sejal 2. Made changes in the data collection. 3. Made 40 prompts for chatbot training 4. Took the feed back from sejal and started working on it from scratch | completed | 1. Worked on time sheet and documentation 2. Tested chatbot and took analysis for dashboard 3. Completed with time sheet and documentation completion. Will do testing by EOD | in progress
3 | Avinash10.Gupta | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the project, analyzed the folder structure, and initiated learning Node Js and Mongo DB | Pending | Collaborated with the team to finalize the authentication page | Completed | Reasearch and development and initial commit of authentication page | Completed | Conducted initial login testing and Merged stage branch with login updates. | Completed | NA |  | NA |  | New changes were introduced so did research about the overall implementation | Pending | Finalized login backend implementation and completed final login integration. | Completed | Conducted final login testing using postman | Completed | provided helping hands for Integrating Backend of the Tournament Page | completed | Documentation | Completed
4 | Bhavya.Momaya | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the Project/Understood the Folder structure/Started Learning Tailwind | Completed | Started with the Layout and Design of Tournaments Page | Pending | Completed the Initial Basic Layout of the Tournament Page and Pushed it | Completed | Debugging | completed | NA |  | NA |  | NA | On Leave | NA | On Leave | Debugging | Completed | Integrated Backend of the Tournament Page | Completed | Started working on Modal Component Enchancements | In Progress
5 | Devraj3.Singh | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Discussed the Layout and design of Login form with Omkar | Completed | Designed the Login form | Completed | Implemented Coach Login form page | Completed | Added error messages | Completed | Discussed the flow of forgot password with Omkar | Completed | NA |  | Designed the Forgot password page flow | Completed | Implemented Forgot Password | Completed | NA |  | NA |  | Changes in Login page UI | Pending
6 | Dhiraj.Kunder | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the project, analyzed the folder structure, and initiated learning Tailwind CSS ,Git and basic React.js. | Completed | Collaborated with the team to finalize the main tournament page design. | Completed | Designed and enhanced the tournament page layout, then pushed the updates to the repository. | Completed | Resolved UI issues related to screen resolution adjustments. | Completed | NA |  | NA |  | Began working on the modal design and conducted research on UI designs based on the Figma reference with the help of umakant and omkar. | In progress | Implemented the Figma design as per the requirements. | completed | Fixed UI issues related to the modal design. | Completed | Added a text area field to accommodate long descriptions in the modal. | completed | Initiated enhancements for the modal component. | In progress
7 | Jaypal.Koli | NA |  | Initial setup | Completed | Worked on UI structure and component breakdown | Completed | Implemented basic tournament creation functionality | Completed | NA |  | NA |  | Integrated API calls for tournaments | Completed | Tested and refined tournament workflow | Completed | Implemented EditTournament Page, Fixed Upload/Edit/Save Button | Completed | UI changes in Image | Completed | Fixed Edit Button Functionality | Completed | NA |  | NA |  | Added functionality Delete Button & Temporary Card | Completed | Small UI Changes of Buttons | completed | Implemented Total Score, Issue Count, & Fixed Alignment | Completed | Tournament Functionality, Update/Delete Features | completed | Changing UI of Tournament page according to Figma | Pending
8 | Manoj.Inbarajan | Started creating Proof of Concept (PoC) for idea validation | Completed | Started creation of Project Charter Document | Completed | Updated Project Charter Document with team discussions | Completed | NA | NA | NA | NA | Created wireframe and shared PoC & Project Charter with stakeholders | Completed | Conducted basic dev walkthrough using wireframe | Completed | Created Product Requirement Document (PRD) | Completed | Updated PRD and gave inputs on development process | Completed | Discussed with Omkar regarding flow of project and update of the same. | Completed | Gave input and accumulated the data related to tournaments. | Completed | NA |  | NA |  | Took stakeholder input for PoC document edits | Completed | Updated PoC from Word to Figma for better usability | completed | On leave | NA | Conducted scrum meeting and took the update of project. | completed | Documentation and sent meeting summary to stakeholders | Pending
9 | Mridul.Upadhya | NA | NA | Worked on User-Story creation for various featues on landing page for both Player and Coach , coach dashboard and team photo page | Completed | Worked on User-Story creation for various featues on Tournament page , score card page and exit page for both Player and Coach | Completed | Refined user stories based on the updated UI components of the project. | Completed |  | NA | Worked on User-Story creation for Chatbot | completed | NA | NA | [16 empty] | Worked on User-Story updation for Chatbot based on the behavior of the bot | completed | Worked on User-Story updation for Chatbot based on the behavior of the bot | completed
11 | Nikita.Suhane | Created a text document on notepad listing the tasks performed after the previous biweekly date i.e. 30 January 2025. | Completed | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Created an Excel sheet by extracting individual members' issue details from the DevOps Issue Tracker. Scores were collected from the App Development CoE Issue Tracker and the MPC Issue Tracker. The sheet includes each team member's scores, issue count, severity assigned, and the specific application for which the issue was raised. | Completed | NA |  | NA |  | NA |  | NA |  | Updated scores and issue count of members. | Completed | Updated scores and issue count of members. | completed | NA |  | Contributed content to be written on the tournaments cards for giving a gist of the applications worked upon , namely NM App Revamp, NaMo Transcript, and NaMo AI, to be displayed on the “tournaments” page. | completed | NA
12 | Omkar.Ghodake | Set up a GitHub repository with boilerplate code and two branches, i.e, stage and production | Completed | Created modal component | Completed | Took project completion report from team members | on leave | Took project completion report from team members | on leave | Took project completion report from team members | on leave | Took project completion report from team members | on leave | Took project completion report from team members | on leave | Took project completion report from team members | on leave | NA | NA | Solved technical problems of team web application | NA | Solved technical problem in ChatBot | Completed | Created form and button components | Pending | Created form and button components | Completed | Solved technical problem in ChatBot | Completed | created schemas | completed | updated schemas, connected frontend and backend | Completed
13 | Rishabh.Kanaujiya | Design Main MPC Logo | Completed | Jersey Design | Completed | NA | On leave | NA | On leave | NA | On leave | NA | On leave | Edited Team Members photos | Completed | NA | On leave | NA | On leave | NA | On leave | NA | On leave | NA | On leave | NA | On leave | 1. Designed the Logos for Tournament Page 2. Developed the API for forgot password | Completed | 1. Designed the frontend of Landing and Exit Page 2. Re-edited images of few team members | Completed | 1. Enhanced the Landing page with new background 2. Integrated GenAI to chat bot frontend | Completed | Fine Tuned the model for Employees Data | completed | 1. Adding the skip button in landing page to skip the video animation 2. Fine tunning of chatbot | In progress
14 | Sakshi1.Rai | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Start working on ML model (Bert) | Inprogress | Start working on ML model (Bert) | Completed | Start working on Different ML model(TF-IDF) | Inprogress | Start working on Different ML model(TF-IDF) | Completed | Start working on Different ML model Cosine Matrix | Inprogress | Start working on Different ML model Cosine Matrix | Completed | NA |  | NA |  | Working on GenAI Model Started working on frontend of Chatbot as per figma | Completed | Enhanced the code of Chatbot and resolve the issues | Completed | Convert Django Model to Node JS Updated the chatbot frontend | Completed | Fine tunning of Chatbot | Inprogress
15 | Sanjeev2.Prajapati | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Start working on ML model (Bert) | Inprogress | Start working on ML model (Bert) | Completed | Start working on Different ML model(TF-IDF) | Inprogress | Start working on Different ML model(TF-IDF) | Completed | Start working on Different ML model Cosine Matrix | Inprogress | Start working on Different ML model Cosine Matrix | Completed | NA |  | NA |  | Working on GenAI Model | Completed | Enhanced the code and resolve the issues | Completed | Convert Django Model to Node JS | Completed | Fine tunning of Chatbot | Inprogress
16 | Shubham2.Joshi
17 | Umakant.Patil | NA | on leave | Start working on Basic 3d backgrond Rotation module design. | Completed | Start working on Sample Background Created | Completed | Start working on Stadium Background Minor changes. | Completed | NA | On leave | NA | on leave | Start working on Team Members Score cards Implementation | Completed | Team Members cards changes as per discussion | Completed | Implemented new design of team members cards as per figma | Completed | Changes in team members card Design | Completed | Implemented Team member Score card Backgraound Clickable | Completed | NA |  | NA |  | Detail of Team member Score card Modal Implemented | Completed | Detail of Score card Modal changes done | completed | Tournaments Modal Changes Implemented as per figma | Completed | 1.Team members project, courses, Switch Feature implemented and also fix bugs. 2. Fetch Data from Backend and minor changes on Backend | completed | Cross button background colour implementation | Inprogress
18 | Vishnu1.Menon | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Implemented Create Tournament Controller | Completed | NA |  | NA |  | Implemented following controllers: 1. Update 2. DeleteOne 3. GetOne 4. GetAll | Completed | Fixed minor issues tested the API's Implemented deleteMany controller | Completed | NA |  | NA |  | NA

## Main TimeSheet
Sr.No | Domain Name | 2025-03-11 |  | 2025-03-12 |  | 2025-03-13 |  | 2025-03-14 |  | 2025-03-15 |  | 2025-03-16 |  | 2025-03-17 |  | 2025-03-18 |  | 2025-03-19 |  | 2025-03-20 |  | 2025-03-21 |  | 2025-03-22 |  | 2025-03-23 |  | 2025-03-24 |  | 2025-03-25 |  | 2025-03-26 |  | 2025-03-27 |  | 2025-03-28 |  | 2025-03-29 |  | 2025-03-30 |  | 2025-03-31 |  | 2025-04-01 |  | 2025-04-02 |  | 2025-04-03 |  | 2025-04-04 |  | 2025-04-05 |  | 2025-04-06 |  | 2025-04-07 |  | 2025-04-08 |  | 2025-04-09
|  | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status | Task implemented | Status
1 | Anagha.Shinde | NA |  | NA | On Leave | NA | On Leave | NA | PH | NA |  | NA |  | Refer the wireframes (low-fidelity)shared by product. | Completed | Ideate the color schemes / theme of the website using the key elements and inputs given, post discussion with product. | Completed | Mid fidelity wireframe implementation | Completed | Design iterations for Player cards | Completed | Design iteration for player cards and player details. Cross communication with frontend devs (Umkant, Shubham) | Completed | NA |  | NA |  | Design iteration for Admin side. 1. Add tournament 2. Add Player | Completed | Discussion of desgin implementation with devs (Umakant, Shubham, Jaypal) Work on feedback and suggestions from the devs. | Completed | Design iteration for Admin side Discussion with devs | In progress | Design disscussions and ideation for credits page | In progress | Design iteration for login: 1.Login Page 2.Forgot Password page: Take email as input 3.Enter OTP page: 6 digit OTP Create new password page: Two 4.input fields: Enter Password and Confirm Password | In progress | NA |  | NA |  | NA | On Leave | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA
2 | Anushree1.Shukla | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA |  | NA |  | NA |  | 1. Had a discussion with Omakr and Sejal regarding my contribution in Bi-Weekly 2. came with ideas for the dashboard of chatbot analysis using MPC and Team Data | Completed | no task implemented |  | no task implemented |  | 1. made sheets for prompts and generated around 100 prompts to run in chatbot in diffrent categories 2. succussfully made 100 prompts in different category for chatbot | Completed | 1. started working on the dashboard with Sanjeev 2. came up with ideas how data can be presented | Completed | 1. Still worked on dashboard on power bi in morning 2. Completed dashboard making by EOD | Completed | 1. Got dashboard reviewed by Sejal 2. Made changes in the data collection. 3. Made 40 prompts for chatbot training 4. Took the feed back from sejal and started working on it from scratch | Completed | 1. Worked on time sheet and documentation 2. Tested chatbot and took analysis for dashboard 3. Completed with time sheet and documentation completion. Will do testing by EOD | In progress | NA |  | NA |  | 1. Tested around 40 prompts 2. Also worked on dashbaord making | In progress | Completed dashboard making. | Completed | made some required changes in the dashboard | completed | NA |  | Updated the dashbaord according to the bugs raised in the team. | completed | NA |  | NA |  | NA |  | NA |  | NA
3 | Avinash10.Gupta | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the project, analyzed the folder structure, and initiated learning Node Js and Mongo DB | In progress | Collaborated with the team to finalize the authentication page | Completed | Reasearch and development and initial commit of authentication page | Completed | Conducted initial login testing and Merged stage branch with login updates. | Completed | NA |  | NA |  | New changes were introduced so did research about the overall implementation | In progress | Finalized login backend implementation and Completed final login integration. | Completed | Conducted final login testing using postman | Completed | provided helping hands for Integrating Backend of the Tournament Page | Completed | Documentation | Completed | NA |  | NA |  | Tested 50 prompts and performs smoke testing for MPC Bot | Completed | Assisted in frontend login and performed smoke testing on MPC bot | Completed | NA |  | Fixed bugs and added the character limit to coach profile | Completed | NA |  | NA |  | NA |  | NA |  | 1. Added data in tournaments card 2. Various bugs fixing | Completed | NA
4 | Bhavya.Momaya | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the Project/Understood the Folder structure/Started Learning Tailwind | Completed | Started with the Layout and Design of Tournaments Page | In progress | Completed the Initial Basic Layout of the Tournament Page and Pushed it | Completed | Debugging | Completed | NA |  | NA |  | NA | On Leave | NA | On Leave | Debugging | Completed | Integrated Backend of the Tournament Page | Completed | Started working on Modal Component Enchancements | In Progress | NA |  | NA |  | Rendered 2 new fields in tournaments page and tested 50 prompts for MPC Bot | Completed | Made frontend layout changes in tournment page and performed smoke testing on MPC Bot | Completed | Performed smoke testing for MPC Bot | completed | NA |  | Minor Frontend Changes | completed | NA |  | NA |  | NA |  | NA |  | NA
5 | Devraj3.Singh | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Discussed the Layout and design of Login form with Omkar | Completed | Designed the Login form | Completed | Implemented Coach Login form page | Completed | Added error messages | Completed | Discussed the flow of forgot password with Omkar | Completed | NA |  | Designed the Forgot password page flow | Completed | Implemented Forgot Password | Completed | NA |  | NA |  | Changes in Login page UI | In progress | NA |  | Created Login form | Pending | Implementation of New Login page | In progress | 1. Updated whole UI of the login page and connected with backend | Completed | Added animation on login page and updated login page image | Completed | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA
6 | Dhiraj.Kunder | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Cloned the project, analyzed the folder structure, and initiated learning Tailwind CSS ,Git and basic React.js. | Completed | Collaborated with the team to finalize the main tournament page design. | Completed | Designed and enhanced the tournament page layout, then pushed the updates to the repository. | Completed | Resolved UI issues related to screen resolution adjustments. | Completed | NA |  | NA |  | Began working on the modal design and conducted research on UI designs based on the Figma reference with the help of umakant and omkar. | In progress | Implemented the Figma design as per the requirements. | Completed | Fixed UI issues related to the modal design. | Completed | Added a text area field to accommodate long descriptions in the modal. | Completed | Initiated enhancements for the modal component. | In progress | NA |  | NA |  | Created login form design as per the figma | Completed | Updated whole UI of the login page and added new component as per new design | Completed | NA |  | Changed font size ,style and added scrollbar in tournaments page | Completed | NA |  | NA |  | NA |  | NA |  | Implemented bold text issue | Completed | Enhanced UI of Edit tournament,tournament,and dashboard | Completed
7 | Jaypal.Koli | NA |  | Initial setup | Completed | Worked on UI structure and component breakdown | Completed | Implemented basic tournament creation functionality | Completed | NA |  | NA |  | Integrated API calls for tournaments | Completed | Tested and refined tournament workflow | Completed | Implemented EditTournament Page, Fixed Upload/Edit/Save Button | Completed | UI changes in Image | Completed | Fixed Edit Button Functionality | Completed | NA |  | NA |  | Added functionality Delete Button & Temporary Card | Completed | Small UI Changes of Buttons | Completed | Implemented Total Score, Issue Count, & Fixed Alignment | Completed | Tournament Functionality, Update/Delete Features | Completed | Changing UI of Tournament page according to Figma | In progress | NA | WO | NA | WO | NA | On Leave | Added tournaments data | Completed | NA |  | 1. Add charcter limit to input field into editTournament Page 2. Image validation into editTournament Page | Completed | NA |  | NA |  | NA |  | NA |  | Two dynamic input field in editTournament | Completed | NA
8 | Manoj.Inbarajan | Started creating Proof of Concept (PoC) for idea validation | Completed | Started creation of Project Charter Document | Completed | Updated Project Charter Document with team discussions | Completed | NA | WO | NA | WO | Created wireframe and shared PoC & Project Charter with stakeholders | Completed | Conducted basic dev walkthrough using wireframe | Completed | Created Product Requirement Document (PRD) | Completed | Updated PRD and gave inputs on development process | Completed | Discussed with Omkar regarding flow of project and update of the same. | Completed | Gave input and accumulated the data related to tournaments. | Completed | NA | WO | NA | WO | Took stakeholder input for PoC document edits | Completed | Updated PoC from Word to Figma for better usability | Completed | On Leave | NA | Conducted scrum meeting and took the update of project. | Completed | Documentation and sent meeting summary to stakeholder | Completed | NA | WO | NA | WO | 1. Created Task in Jira and updated accordingly after scrum. 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Created Task in Jira and updated accordingly after scrum. 2. Checked in with data analyst to monitor progress and suggest necessary feedbacks 3. Executed prompt testing for MPC Chatbot. | Completed | 1. Created Task in Jira and updated accordingly after scrum. 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Created Task in Jira and updated accordingly after scrum. 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Created Task in Jira and updated accordingly after scrum. 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | NA |  | NA |  | NA |  | NA |  | NA
9 | Mridul.Upadhya | Discussed with Developers for the feasibility of already planned features and what more innovative we can do . | Completed | Worked on User-Story creation for various featues on landing page for both Player and Coach , coach dashboard and team photo page | Completed | Worked on User-Story creation for various featues on Tournament page , score card page and exit page for both Player and Coach | Completed | Refined user stories based on the updated UI components of the project. | Completed | NA | NA | Worked on User-Story creation for Chatbot | Completed | NA | NA | NA | NA | Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | NA | NA | NA |  | NA |  | NA |  | Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | Worked on User-Story updation for Chatbot based on the behavior of the bot | Completed | Worked on User-Story updation for Chatbot based on the behavior of the bot | Completed | Conducted scrum call to gather progress on already assigned tasks and clarify tasks that need to be Completed before EOD | Completed | NA |  | NA |  | 1. Created scrum report 2. Updated User Stories 3. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Updated User Stories 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Created an epic for the project . 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | 1. Ask the developers to review the user story and provide relevant feedback. 2. Checked in with developers to monitor progress and suggest necessary feedbacks | Completed | NA |  | NA |  | NA |  | NA |  | NA
10 | Nikita.Suhane | Created a text document on notepad listing the tasks performed after the previous biweekly date i.e. 30 January 2025. | Completed | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | Started creating Excel sheet related to issue count and scores of individual members | Completed | Created an Excel sheet by extracting individual members' issue details from the DevOps Issue Tracker. Scores were collected from the App Development CoE Issue Tracker and the MPC Issue Tracker. The sheet includes each team member's scores, issue count, severity assigned, and the specific application for which the issue was raised. | Completed | NA |  | NA |  | NA |  | NA |  | Updated scores and issue count of members. | Completed | Updated scores and issue count of members. | Completed | NA |  | Contributed content to be written on the tournaments cards for giving a gist of the applications worked upon , namely NM App Revamp, NaMo Transcript, and NaMo AI, to be displayed on the “tournaments” page. | Completed | On Leave |  | NA |  | NA |  | 1. Added content related to "Test case regression" in the Excel sheet; 2. Updated issue count and scores | Completed | 1. Executed testing over 50 prompts for MPC Chatbot 2. Updated scores and issue count of members. 3. Provided data regarding issues for dashboard | Completed | Updated scores and issue count of members. | Completed | NA |  | NA |  | NA |  | NA |  | Updated scores and issue count of members. | Completed | NA |  | NA
11 | Omkar.Ghodake | Set up a GitHub repository with boilerplate code and two branches, i.e, stage and production | Completed | Created modal component | Completed | Took project completion report from team members | On Leave | Took project completion report from team members | On Leave | Took project completion report from team members | On Leave | Took project completion report from team members | On Leave | Took project completion report from team members | On Leave | Took project completion report from team members | On Leave | NA | NA | Solved technical problems of team web application | NA | Solved technical problem in ChatBot | Completed | Created form and button components | In progress | Created form and button components | Completed | Solved technical problem in ChatBot | Completed | created schemas | Completed | updated schemas, connected frontend and backend | Completed | Created navbar and added protected routes | Completed | Updated navbar and form components | In progress |  |  | Completed reset password backend | Completed | Reset password fixtures | Completed | 1.Connected landing page to the backend 2. Updated the UI of Landing page 3. Updated modal | Completed | 1.Solved techincal problems | Completed | Fixed bugs | Completed | Fixed bugs | Completed | NA |  | Created file directory | In Progress | File directory | Completed | Fix login page bugs, | Completed | Resolved edit tournament bugs and updated document files | Complete
12 | Rishabh.Kanaujiya | Design Main MPC Logo | Completed | Jersey Design | Completed | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | Edited Team Members photos | Completed | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | NA | On Leave | 1. Designed the Logos for Tournament Page 2. Developed the API for forgot password | Completed | 1. Designed the frontend of Landing and Exit Page 2. Re-edited images of few team members | Completed | 1. Enhanced the Landing page with new background 2. Integrated GenAI to chat bot frontend | Completed | Fine Tuned the model for Employees Data | Completed | 1. Adding the skip button in landing page to skip the video animation 2. Fine tunning of chatbot | In progress | NA |  | NA |  | Fine tuning of Chatbot | Completed | Added some more data in the chatbot,fine tuning of chatbot and re-edited some more pictures for the website | Completed | 1. Fine Tuning of Chatbot for managers data 2. Generated New Jersey and image for coach | Completed | Fine tunned model in managers data | Inprogress | Fine tunned model in managers data | Completed | NA |  | NA |  | NA | NA | Score updation | Completed | NA
13 | Sakshi1.Rai | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Start working on ML model (Bert) | In progress | Start working on ML model (Bert) | Completed | Start working on Different ML model(TF-IDF) | In progress | Start working on Different ML model(TF-IDF) | Completed | Start working on Different ML model Cosine Matrix | In progress | Start working on Different ML model Cosine Matrix | Completed | NA |  | NA |  | Working on GenAI Model Started working on frontend of Chatbot as per figma | Completed | Enhanced the code of Chatbot and resolve the issues | Completed | Convert Django Model to Node JS Updated the chatbot frontend | Completed | Fine tuning of Chatbot | In progress | NA |  | NA |  | Fine tuning of Chatbot | Completed | 1.Added Scroll bar in the Chatbot 2. Added functionality to send one prompt at a time | Completed | Fine tuning of Chatbot | Completed | NA |  | NA |  | NA |  | NA |  | NA |  | Added Default Prompts in Chatbot | Completed | NA
14 | Sanjeev2.Prajapati | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Start working on ML model (Bert) | In progress | Start working on ML model (Bert) | Completed | Start working on Different ML model(TF-IDF) | In progress | Start working on Different ML model(TF-IDF) | Completed | Start working on Different ML model Cosine Matrix | In progress | Start working on Different ML model Cosine Matrix | Completed | NA |  | NA |  | Working on GenAI Model | Completed | Enhanced the code and resolve the issues | Completed | Convert Django Model to Node JS | Completed | Fine tuning of Chatbot | In progress |  |  |  |  | Fine tuning of Chatbot | Completed | Fine tuning of chatbot and worked on Power Bi dashboard | Completed | Fine tuning of Chatbot | Completed | Fine tunned model in managers data | Inprogress | Fine tunned model in managers data | Completed | NA |  | NA |  | NA |  | Score updation | Completed | NA
15 | Shubham2.Joshi | Discussing the flow of project and start with editing the basic boiler plate code | Completed | Create scorelist component that renders for each player | Completed | Create Tournaments page | Completed | Create TournamentCard component | Completed | NA |  | NA |  | Start with Creating form for EditPlayers page | In progress | Setup of Image upload and save to cloud API | Completed | Discussed changes an enhancements with tech lead and product | Completed | Search for backgrounds for all admin pages | Completed | Complete the EditPlayer form | Completed | NA |  | NA |  | Added coach model and integrated Image uploading API in all the APIs | Completed | Tested & Edited the controllers of EditPlayer and EditTournament APIs through Postman | Completed | Discussed the Redesign of admin pages forms and started with initial developement | Completed | Connect Tournament APIs to backend, add toast notifications | Completed | Started working on EditCoach form and editTeam form | In progress | Created Input component and Started implementation of redesigned EditPlayer form | In progress | Connected the new editPlayer APIs to Backend and fixed important issues | Completed | Completed the editPlayer form,editTeam form, some bug fixes and enhancements | Completed | Added back buttons to all dashboard pages and changed scrollbar styles | Completed | Changes in modal to adjust according to screen sizes | Completed | Added character limit in forms and validations to images | Completed | Connected Coach Page to Backend and some minor changes | Completed | NA |  | NA |  | NA |  | Back Button changed and minor issues fixed | Completed | NA
16 | Umakant.Patil | NA | On Leave | Start working on Basic 3d backgrond Rotation module design. | Completed | Start working on Sample Background Created | Completed | Start working on Stadium Background Minor changes. | Completed | NA | On Leave | NA | On Leave | Start working on Team Members Score cards Implementation | Completed | Team Members cards changes as per discussion | Completed | Implemented new design of team members cards as per figma | Completed | Changes in team members card Design | Completed | Implemented Team member Score card Backgraound Clickable | Completed | NA |  | NA |  | Detail of Team member Score card Modal Implemented | Completed | Detail of Score card Modal changes done | Completed | Tournaments Modal Changes Implemented as per figma | Completed | 1.Team members project, courses, Switch Feature implemented and also fix bugs. 2. Fetch Data from Backend and minor changes on Backend | Completed | Cross button background colour implementation | Completed | NA |  | NA |  | 1. Team Members updated data is added and also done minor changes 2. Scroll bar added in Team member details | Completed | Fix Team member Rank issue and also done minor changes | Completed | Credits page implemented | Completed | Credit Page background implemented and fix some minor changes | Completed | NA |  | NA |  | NA |  | NA |  | Team member score card Scrollbar minor issues fix | Completed | NA
17 | Vishnu1.Menon | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | Implemented Create Tournament Controller | Completed | NA |  | NA |  | Implemented following controllers: 1. Update 2. DeleteOne 3. GetOne 4. GetAll | Completed | Fixed minor issues tested the API's Implemented deleteMany controller | Completed | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA

## Course & Task
Name | Course | Personal Projects Title | Personal Documentation Link
Anagha Shinde | Web Design: Wireframes to Prototypes Autolayouts in Figma | 1. UI Case Study: IRCTC Revamp 2. Crochet Instgram Store Webpage | Anagha.Shinde
Anushree Shukla | Google Analyst Courses PowerBi in Data Analyst | 1. Pizza Sales Analysis 2. Retail Store Dashboard | Anushree1.Shukla
Avinash Gupta | Backend , SprintBoot, Javascript | Reimbursement System | Avinash10.Gupta
Bhavya Momaya | 1. JavaScript 2. React Js | Image Editior using Vanilla Js | Bhavya Momaya
Devraj Singh | Master Spring Boot 3 & Spring Framework 6 with Java | E-commerce website | Devraj3.Singh
Dhiraj Kunder | 1. JavaScript basics 2. Tailwind CSS | Signature verification | DhirajKunder
Jaypal Koli | Java: Testing with JUnit Postman Essential Training | Personal Portfolio website | Link
Manoj Inbarajan | 1. Completed six IBM Product Management courses and earned a professional certification. 2.Power BI. 3.Practice Exam for AIPMM Certified Product Manager (CPM) | Product Case Study - JioPOSLite Documentation of: - Product Requirement Document (PRD) - Project Charter - Proof of Concept (PoC) | Manoj_Inbarajan
Mridul Upadhya | 1. Mern stack 2. Product Management* | Full stack E-commerce website | Mridul.Upadhya
Nikita Sonawane | Java, Spring, Spring Boot | E-commerce website Construction and Demolition Waste Management System | Nikita.Sonawane
Nikita Suhane | Introduction to Secure Networking, Security Operations Center | NA | Nikita.Suhane
Omkar Ghodake | Blockchain | Custom UI libraries, DEX | Omkar.Ghodake
Rishabh Kanaujiya | React Native , Web Scraping | DSA Helper , Menu Extractor | Rishabh.Kanaujiya
Sakshi Rai | Data Science Course | 1. Commerce Customer Churn Analysis and Prediction 2.Market Basket Analysis using Unsupervised K-Means Clustering | Sakshi1.Rai
Sanjeev Prajapati | Machine Learning,Deep Learning | Chatbot using genAI Social Network classification using DecisionTreeClassifier | Sanjeev2.Prajapti
Shubham Joshi | 1. React.js 2. Node.js | 1. User based video sharing platform 2. User based platform to Create, Edit & Read Blogs | Shubham2.Joshi
Umakant Patil | Backend With Java. Spring Data Repositories. | Employee Tracker using SpringBoot | Umakant.Patil
Vishnu Menon | Go Routines and Concurrency Redis Docker | 1. Video-Ad player 2. URL Shortner | Vishnu1.Menon

## Assigned to
Sr. no | Pages | Frontend |  | Backend
|  | Component | Assigned to | Component | Assigned to
1 | Landing | MPC Logo | Umakant.Patil Omkar.Ghodake
Animated Background
MPC Information Section
Navigation/Redirection Buttons
2 | Login (coach) | Form | Devraj3.Singh | User authentication | Avinash10.Gupta
3 | Team photo | Team photo with jersey | Rishabh.Kanaujiya | Get image
Animated Background Layer
4 | Tournaments | Tournament Logos | Dhiraj.Kunder Bhavya.Momaya | Get images
|  | Tournament Card Components |  | Get tournaments info
Tournament Modal Dialog
Navigation/Redirection Buttons
5 | Score | Individual Cutout Images | Umakant.Patil | Get Images
|  | Details Modal Dialog |  | Get players Info
Navigation/Redirection Buttons
6 | Dashboard | CRUD Operations Interface |  | User authorisation
7 | Players CRUD | Team Data Table View | Shubham2.Joshi | Players CRUD
|  | CRUD Form Modal |  | Images CRUD
8 | Tournament CRUD | Tournament Grid Layouts | Shubham2.Joshi | Tournaments CRUD | Vishnu1.Menon
|  | CRUD Form Modal | Jaypal.Koli | Images CRUD
9 | Team CRUD | RUD (Read, Update, Delete) Operations |  | Team RUD

## Daily Progression (hidden)
Sr. no | Pages | Frontend | Backend | 3/11/2025 | 3/12/2025 | Column1 | Column2 | Column3
1 | Black | Black screen |  | Done
2 | Landing | MPC Logo |  | Designed logos with multiple designs for MPC
|  | Animated Background |  | Ideation for background animation
Information about MPC
Redirection buttons
3 | Login (coach) | Form | User authentication
4 | Team photo | Team photo with jersey | Get image
Animated background
5 | Tournaments | Tournament Logos | Get images
|  | Tournament Cards | Get tournaments info
Tournament Modal
Redirection buttons
6 | Score | Cutout of individuals | Get Images
|  | Details Modal | Get players Info
Redirection buttons
7 | Dashboard | Options to CRUD | User authorisation
8 | Players CRUD | Team Table view | Players CRUD
|  | CRUD form Modal | Images CRUD
9 | Tournament CRUD | Grids for Tournaments | Tournaments CRUD
|  | CRUD form Modal | Images CRUD
10 | Team CRUD | Options to RUD | Team RUD
11 | User story |  |  | Written user story
12 | Wireframe |  |  | Ideation of wireframe for player/Coach view